## Data
Task ID | Task Name | Start Date | Due Date | Project | Owner | Status | Priority | % Complete
TSK-1001 | Optimize data pipeline | 2026-01-05 | 2026-02-02 | Mobile App Launch | Aditi Sharma | In Progress | High | 28
TSK-1002 | Analyze campaign assets | 2026-01-25 | 2026-02-06 | Mobile App Launch | Arjun Kapoor | Not Started | Medium | 0
TSK-1003 | Review third-party integration | 2026-04-19 | 2026-05-07 | Website Revamp | Neha Gupta | Completed | Low | 100
TSK-1004 | Test dashboard layout | 2026-03-19 | 2026-04-03 | Marketing Automation | Aditi Sharma | In Progress | High | 50
TSK-1005 | Deploy API endpoints | 2026-02-27 | 2026-03-23 | Q3 Product Release | Rohan Mehta | Not Started | Low | 0
TSK-1006 | Plan campaign assets | 2025-12-21 | 2026-01-12 | Vendor Onboarding | Neha Gupta | Delayed | Low | 38
TSK-1007 | Deploy database schema | 2026-01-28 | 2026-02-26 | Q3 Product Release | Arjun Kapoor | Not Started | Low | 0
TSK-1008 | Document dashboard layout | 2026-03-04 | 2026-03-14 | Cloud Infra Upgrade | Rohan Mehta | In Progress | Medium | 62
TSK-1009 | Configure backup process | 2026-02-01 | 2026-02-11 | Marketing Automation | Rohan Mehta | In Progress | Medium | 74
TSK-1010 | Train test cases | 2026-01-28 | 2026-02-03 | Cloud Infra Upgrade | Vikram Singh | Completed | High | 100
TSK-1011 | Review performance metrics | 2026-04-25 | 2026-05-22 | Data Warehouse Build | Sneha Iyer | Delayed | Low | 40
TSK-1012 | Audit access controls | 2026-04-23 | 2026-05-15 | Data Warehouse Build | Farhan Khan | In Progress | Low | 48
TSK-1013 | Develop API endpoints | 2026-01-05 | 2026-01-26 | Data Warehouse Build | Arjun Kapoor | In Progress | Medium | 78
TSK-1014 | Develop user feedback | 2026-03-19 | 2026-04-12 | Mobile App Launch | Priya Nair | Completed | Medium | 100
TSK-1015 | Optimize user authentication | 2026-04-21 | 2026-04-26 | Data Warehouse Build | Arjun Kapoor | Completed | Critical | 100
TSK-1016 | Analyze reporting module | 2026-03-27 | 2026-04-01 | Marketing Automation | Vikram Singh | In Progress | Low | 48
TSK-1017 | Document reporting module | 2026-01-20 | 2026-01-29 | Mobile App Launch | Sneha Iyer | Completed | High | 100
TSK-1018 | Deploy security policies | 2026-03-03 | 2026-04-02 | Website Revamp | Arjun Kapoor | Not Started | Medium | 0
TSK-1019 | Plan database schema | 2025-12-22 | 2026-01-19 | Website Revamp | Karan Verma | Delayed | High | 51
TSK-1020 | Plan campaign assets | 2026-01-12 | 2026-01-25 | CRM Migration | Priya Nair | Delayed | High | 53
TSK-1021 | Deploy user feedback | 2026-01-21 | 2026-02-17 | Data Warehouse Build | Karan Verma | Completed | Critical | 100
TSK-1022 | Document UI mockups | 2026-02-02 | 2026-02-14 | Q3 Product Release | Farhan Khan | In Progress | High | 23
TSK-1023 | Develop API endpoints | 2025-12-16 | 2025-12-28 | Cloud Infra Upgrade | Arjun Kapoor | Not Started | Low | 0
TSK-1024 | Test access controls | 2026-04-04 | 2026-04-15 | Q3 Product Release | Rohan Mehta | In Progress | Medium | 84
TSK-1025 | Optimize onboarding flow | 2026-01-18 | 2026-01-26 | Vendor Onboarding | Karan Verma | Blocked | High | 16
TSK-1026 | Optimize user authentication | 2025-12-14 | 2026-01-09 | Q3 Product Release | Anjali Rao | Blocked | Medium | 51
TSK-1027 | Review data pipeline | 2025-12-28 | 2026-01-09 | Website Revamp | Anjali Rao | Blocked | High | 22
TSK-1028 | Train data pipeline | 2026-02-02 | 2026-02-09 | Vendor Onboarding | Priya Nair | In Progress | Medium | 71
TSK-1029 | Finalize security policies | 2025-12-04 | 2025-12-11 | Mobile App Launch | Aditi Sharma | Completed | High | 100
TSK-1030 | Configure UI mockups | 2026-03-13 | 2026-03-19 | CRM Migration | Anjali Rao | In Progress | Medium | 36
TSK-1031 | Audit data pipeline | 2026-02-12 | 2026-03-02 | Data Warehouse Build | Sneha Iyer | Completed | Critical | 100
TSK-1032 | Design test cases | 2025-12-15 | 2026-01-07 | Vendor Onboarding | Priya Nair | In Progress | Low | 84
TSK-1033 | Design email templates | 2026-04-15 | 2026-04-25 | Website Revamp | Aditi Sharma | Completed | Medium | 100
TSK-1034 | Develop access controls | 2026-01-30 | 2026-02-16 | Mobile App Launch | Priya Nair | Not Started | Low | 0
TSK-1035 | Migrate access controls | 2026-03-18 | 2026-04-13 | Cloud Infra Upgrade | Arjun Kapoor | Completed | Medium | 100
TSK-1036 | Configure payment gateway | 2026-01-31 | 2026-02-13 | Q3 Product Release | Sneha Iyer | Completed | Low | 100
TSK-1037 | Integrate campaign assets | 2025-12-19 | 2025-12-24 | Marketing Automation | Farhan Khan | Completed | Medium | 100
TSK-1038 | Finalize database schema | 2026-01-03 | 2026-01-19 | Mobile App Launch | Rohan Mehta | Completed | Medium | 100
TSK-1039 | Migrate email templates | 2026-04-19 | 2026-05-16 | Cloud Infra Upgrade | Vikram Singh | In Progress | Medium | 53
TSK-1040 | Develop user authentication | 2026-01-04 | 2026-01-17 | Website Revamp | Neha Gupta | Completed | Medium | 100
TSK-1041 | Analyze performance metrics | 2026-02-26 | 2026-03-09 | CRM Migration | Sneha Iyer | In Progress | Medium | 48
TSK-1042 | Document payment gateway | 2026-02-09 | 2026-02-15 | Marketing Automation | Aditi Sharma | In Progress | Low | 15
TSK-1043 | Design user authentication | 2026-03-20 | 2026-04-11 | Marketing Automation | Priya Nair | Completed | High | 100
TSK-1044 | Configure payment gateway | 2026-04-29 | 2026-05-21 | Mobile App Launch | Priya Nair | Blocked | Medium | 19
TSK-1045 | Optimize security policies | 2025-12-11 | 2025-12-27 | Website Revamp | Sneha Iyer | Delayed | Medium | 33
TSK-1046 | Test security policies | 2026-03-15 | 2026-04-08 | Mobile App Launch | Vikram Singh | Delayed | High | 67
TSK-1047 | Finalize onboarding flow | 2026-02-24 | 2026-03-26 | CRM Migration | Priya Nair | Not Started | High | 0
TSK-1048 | Plan performance metrics | 2026-03-08 | 2026-03-14 | Cloud Infra Upgrade | Sneha Iyer | Completed | Low | 100
TSK-1049 | Review UI mockups | 2026-02-17 | 2026-03-19 | Cloud Infra Upgrade | Karan Verma | In Progress | High | 44
TSK-1050 | Analyze user feedback | 2026-02-10 | 2026-02-26 | Cloud Infra Upgrade | Anjali Rao | Blocked | Medium | 51
TSK-1051 | Design user authentication | 2026-01-15 | 2026-02-07 | Q3 Product Release | Aditi Sharma | Delayed | Low | 36
TSK-1052 | Finalize access controls | 2026-04-10 | 2026-04-18 | Data Warehouse Build | Vikram Singh | In Progress | High | 64
TSK-1053 | Optimize dashboard layout | 2026-04-13 | 2026-05-13 | Cloud Infra Upgrade | Sneha Iyer | In Progress | Low | 83
TSK-1054 | Document user authentication | 2026-02-23 | 2026-03-19 | Q3 Product Release | Anjali Rao | Completed | Low | 100
TSK-1055 | Analyze payment gateway | 2026-03-14 | 2026-04-10 | Marketing Automation | Neha Gupta | In Progress | Medium | 52
TSK-1056 | Deploy user feedback | 2026-01-14 | 2026-02-07 | Cloud Infra Upgrade | Anjali Rao | In Progress | High | 87
TSK-1057 | Integrate third-party integration | 2026-04-28 | 2026-05-22 | Website Revamp | Sneha Iyer | In Progress | Medium | 56
TSK-1058 | Develop server setup | 2026-01-13 | 2026-02-08 | Vendor Onboarding | Karan Verma | Completed | Medium | 100
TSK-1059 | Train dashboard layout | 2026-02-18 | 2026-03-02 | Q3 Product Release | Rohan Mehta | Completed | High | 100
TSK-1060 | Finalize access controls | 2025-12-19 | 2026-01-07 | CRM Migration | Aditi Sharma | Delayed | Low | 46
TSK-1061 | Train onboarding flow | 2025-12-02 | 2025-12-31 | Cloud Infra Upgrade | Anjali Rao | In Progress | Medium | 28
TSK-1062 | Analyze security policies | 2026-03-29 | 2026-04-04 | Cloud Infra Upgrade | Priya Nair | Completed | High | 100
TSK-1063 | Train third-party integration | 2026-04-15 | 2026-05-07 | Mobile App Launch | Farhan Khan | In Progress | Low | 55
TSK-1064 | Train security policies | 2026-04-01 | 2026-04-20 | Data Warehouse Build | Neha Gupta | In Progress | Medium | 48
TSK-1065 | Review backup process | 2026-03-23 | 2026-03-30 | Marketing Automation | Neha Gupta | In Progress | Medium | 51
TSK-1066 | Configure payment gateway | 2026-01-08 | 2026-01-20 | Q3 Product Release | Vikram Singh | Not Started | High | 0
TSK-1067 | Review onboarding flow | 2026-03-30 | 2026-04-17 | Cloud Infra Upgrade | Rohan Mehta | In Progress | Medium | 22
TSK-1068 | Integrate UI mockups | 2026-04-27 | 2026-05-14 | Data Warehouse Build | Arjun Kapoor | Not Started | Critical | 0
TSK-1069 | Audit data pipeline | 2026-03-18 | 2026-04-09 | Q3 Product Release | Sneha Iyer | Blocked | High | 57
TSK-1070 | Optimize user feedback | 2025-12-08 | 2025-12-25 | Cloud Infra Upgrade | Farhan Khan | In Progress | Low | 58
TSK-1071 | Configure access controls | 2026-04-16 | 2026-04-21 | CRM Migration | Farhan Khan | Delayed | Critical | 78
TSK-1072 | Deploy user feedback | 2026-03-29 | 2026-04-08 | Website Revamp | Rohan Mehta | In Progress | Medium | 21
TSK-1073 | Deploy database schema | 2026-03-08 | 2026-03-21 | Q3 Product Release | Karan Verma | In Progress | Medium | 68
TSK-1074 | Optimize database schema | 2026-02-28 | 2026-03-12 | Vendor Onboarding | Aditi Sharma | Not Started | High | 0
TSK-1075 | Review payment gateway | 2025-12-06 | 2025-12-30 | Website Revamp | Aditi Sharma | In Progress | Critical | 34
TSK-1076 | Test campaign assets | 2026-02-04 | 2026-03-05 | Vendor Onboarding | Rohan Mehta | In Progress | Medium | 62
TSK-1077 | Optimize user feedback | 2025-12-07 | 2025-12-21 | Mobile App Launch | Priya Nair | In Progress | Critical | 88
TSK-1078 | Audit server setup | 2026-02-01 | 2026-02-09 | Data Warehouse Build | Karan Verma | Completed | Low | 100
TSK-1079 | Develop email templates | 2026-03-20 | 2026-04-15 | Mobile App Launch | Arjun Kapoor | In Progress | High | 62
TSK-1080 | Optimize third-party integration | 2025-12-28 | 2026-01-15 | Q3 Product Release | Aditi Sharma | Blocked | High | 33
TSK-1081 | Train data pipeline | 2026-02-08 | 2026-03-04 | CRM Migration | Anjali Rao | Completed | Low | 100
TSK-1082 | Plan security policies | 2026-02-07 | 2026-02-22 | Vendor Onboarding | Farhan Khan | Completed | Medium | 100
TSK-1083 | Document UI mockups | 2026-03-29 | 2026-04-21 | Mobile App Launch | Sneha Iyer | In Progress | High | 63
TSK-1084 | Finalize campaign assets | 2026-02-05 | 2026-02-20 | Vendor Onboarding | Vikram Singh | In Progress | Low | 50
TSK-1085 | Configure performance metrics | 2025-12-22 | 2026-01-03 | Marketing Automation | Neha Gupta | Delayed | Low | 66
TSK-1086 | Review user feedback | 2025-12-05 | 2025-12-12 | Cloud Infra Upgrade | Farhan Khan | In Progress | Medium | 52
TSK-1087 | Configure data pipeline | 2026-04-21 | 2026-05-12 | Cloud Infra Upgrade | Sneha Iyer | In Progress | High | 59
TSK-1088 | Audit dashboard layout | 2026-02-03 | 2026-02-15 | Q3 Product Release | Vikram Singh | In Progress | High | 30
TSK-1089 | Audit performance metrics | 2026-01-17 | 2026-01-28 | Q3 Product Release | Rohan Mehta | Delayed | High | 33
TSK-1090 | Plan dashboard layout | 2026-02-11 | 2026-02-19 | Marketing Automation | Arjun Kapoor | Completed | Critical | 100
TSK-1091 | Design API endpoints | 2026-04-16 | 2026-04-25 | Marketing Automation | Karan Verma | In Progress | Medium | 50
TSK-1092 | Migrate server setup | 2025-12-27 | 2026-01-01 | Marketing Automation | Priya Nair | Completed | Medium | 100
TSK-1093 | Develop database schema | 2025-12-14 | 2025-12-27 | Vendor Onboarding | Farhan Khan | In Progress | Medium | 76
TSK-1094 | Test access controls | 2025-12-14 | 2025-12-23 | Data Warehouse Build | Farhan Khan | Completed | Low | 100
TSK-1095 | Train email templates | 2026-03-17 | 2026-04-10 | Marketing Automation | Rohan Mehta | In Progress | Critical | 43
TSK-1096 | Migrate campaign assets | 2026-04-30 | 2026-05-18 | Data Warehouse Build | Farhan Khan | In Progress | Critical | 54
TSK-1097 | Review backup process | 2026-01-23 | 2026-02-17 | Website Revamp | Arjun Kapoor | Not Started | Critical | 0
TSK-1098 | Configure third-party integration | 2026-01-10 | 2026-01-15 | Mobile App Launch | Priya Nair | Completed | Low | 100
TSK-1099 | Develop security policies | 2026-02-11 | 2026-03-10 | Vendor Onboarding | Sneha Iyer | In Progress | Low | 73
TSK-1100 | Review payment gateway | 2026-03-19 | 2026-03-27 | Marketing Automation | Arjun Kapoor | Delayed | High | 54
TSK-1101 | Finalize server setup | 2026-02-17 | 2026-03-13 | Marketing Automation | Priya Nair | In Progress | Low | 87
TSK-1102 | Analyze performance metrics | 2026-03-14 | 2026-03-27 | Vendor Onboarding | Rohan Mehta | In Progress | Medium | 79
TSK-1103 | Design database schema | 2026-02-21 | 2026-03-17 | Vendor Onboarding | Rohan Mehta | Delayed | Medium | 36
TSK-1104 | Design reporting module | 2026-02-07 | 2026-03-02 | Cloud Infra Upgrade | Arjun Kapoor | Not Started | Medium | 0
TSK-1105 | Optimize performance metrics | 2026-01-16 | 2026-02-08 | Vendor Onboarding | Neha Gupta | Delayed | High | 47
TSK-1106 | Configure performance metrics | 2025-12-27 | 2026-01-06 | Mobile App Launch | Farhan Khan | In Progress | Medium | 57
TSK-1107 | Document backup process | 2026-03-27 | 2026-04-03 | Marketing Automation | Anjali Rao | Completed | High | 100
TSK-1108 | Integrate onboarding flow | 2026-04-11 | 2026-04-16 | Q3 Product Release | Rohan Mehta | In Progress | Critical | 84
TSK-1109 | Integrate API endpoints | 2026-04-07 | 2026-05-02 | Website Revamp | Karan Verma | Completed | Medium | 100
TSK-1110 | Develop UI mockups | 2026-03-23 | 2026-04-19 | Cloud Infra Upgrade | Sneha Iyer | Delayed | Medium | 51
TSK-1111 | Review user authentication | 2026-03-15 | 2026-03-22 | Cloud Infra Upgrade | Priya Nair | Not Started | Medium | 0
TSK-1112 | Configure performance metrics | 2026-02-13 | 2026-03-06 | Vendor Onboarding | Rohan Mehta | In Progress | Medium | 49
TSK-1113 | Audit payment gateway | 2026-01-18 | 2026-02-11 | Vendor Onboarding | Karan Verma | In Progress | Medium | 80
TSK-1114 | Deploy UI mockups | 2026-02-26 | 2026-03-28 | Mobile App Launch | Sneha Iyer | Blocked | High | 42
TSK-1115 | Integrate data pipeline | 2026-04-05 | 2026-04-14 | Marketing Automation | Sneha Iyer | Completed | High | 100
TSK-1116 | Finalize test cases | 2026-03-07 | 2026-03-26 | Vendor Onboarding | Vikram Singh | Completed | Medium | 100
TSK-1117 | Audit performance metrics | 2026-03-16 | 2026-03-22 | Cloud Infra Upgrade | Karan Verma | In Progress | Medium | 55
TSK-1118 | Design payment gateway | 2026-01-08 | 2026-01-28 | Data Warehouse Build | Anjali Rao | Completed | Critical | 100
TSK-1119 | Audit payment gateway | 2026-04-14 | 2026-05-03 | Q3 Product Release | Rohan Mehta | In Progress | High | 16
TSK-1120 | Migrate user feedback | 2026-02-06 | 2026-02-21 | Data Warehouse Build | Priya Nair | Completed | Low | 100
TSK-1121 | Audit performance metrics | 2026-03-08 | 2026-03-23 | Mobile App Launch | Vikram Singh | Blocked | High | 50
TSK-1122 | Audit database schema | 2026-02-12 | 2026-02-24 | Website Revamp | Arjun Kapoor | Completed | Low | 100
TSK-1123 | Test server setup | 2025-12-26 | 2026-01-14 | Data Warehouse Build | Rohan Mehta | Completed | High | 100
TSK-1124 | Configure payment gateway | 2026-03-02 | 2026-03-18 | Website Revamp | Aditi Sharma | Not Started | Medium | 0
TSK-1125 | Test database schema | 2026-01-16 | 2026-01-26 | Cloud Infra Upgrade | Neha Gupta | Completed | Medium | 100
TSK-1126 | Integrate backup process | 2026-04-29 | 2026-05-08 | Data Warehouse Build | Arjun Kapoor | In Progress | High | 44
TSK-1127 | Analyze reporting module | 2026-03-30 | 2026-04-13 | Vendor Onboarding | Sneha Iyer | Delayed | High | 63
TSK-1128 | Audit backup process | 2026-02-15 | 2026-03-12 | Mobile App Launch | Farhan Khan | Delayed | Critical | 47
TSK-1129 | Configure access controls | 2026-04-03 | 2026-04-11 | Vendor Onboarding | Sneha Iyer | In Progress | Low | 45
TSK-1130 | Configure backup process | 2025-12-06 | 2026-01-01 | Q3 Product Release | Arjun Kapoor | Completed | Medium | 100
TSK-1131 | Audit performance metrics | 2025-12-13 | 2026-01-06 | Website Revamp | Arjun Kapoor | Completed | High | 100
TSK-1132 | Optimize payment gateway | 2026-01-18 | 2026-02-11 | Marketing Automation | Karan Verma | In Progress | Medium | 47
TSK-1133 | Develop server setup | 2026-04-28 | 2026-05-14 | Mobile App Launch | Aditi Sharma | In Progress | Medium | 31
TSK-1134 | Analyze backup process | 2026-04-18 | 2026-05-04 | Q3 Product Release | Anjali Rao | In Progress | Low | 82
TSK-1135 | Document user authentication | 2026-02-14 | 2026-03-14 | CRM Migration | Sneha Iyer | Delayed | Critical | 75
TSK-1136 | Document database schema | 2026-03-12 | 2026-04-11 | Vendor Onboarding | Rohan Mehta | Delayed | Low | 55
TSK-1137 | Migrate user feedback | 2026-03-05 | 2026-03-31 | Data Warehouse Build | Aditi Sharma | In Progress | Medium | 48
TSK-1138 | Optimize database schema | 2026-04-23 | 2026-05-08 | Q3 Product Release | Rohan Mehta | In Progress | High | 43
TSK-1139 | Integrate user authentication | 2025-12-12 | 2025-12-18 | Vendor Onboarding | Sneha Iyer | In Progress | Medium | 53
TSK-1140 | Configure access controls | 2026-03-27 | 2026-04-12 | Mobile App Launch | Karan Verma | In Progress | High | 84
TSK-1141 | Audit release notes | 2026-03-15 | 2026-03-28 | CRM Migration | Anjali Rao | Blocked | High | 12
TSK-1142 | Analyze release notes | 2026-03-03 | 2026-03-11 | Cloud Infra Upgrade | Farhan Khan | In Progress | Medium | 62
TSK-1143 | Review campaign assets | 2026-03-27 | 2026-04-03 | Website Revamp | Anjali Rao | Delayed | Medium | 62
TSK-1144 | Review database schema | 2026-01-02 | 2026-02-01 | Website Revamp | Aditi Sharma | In Progress | High | 87
TSK-1145 | Train campaign assets | 2026-02-23 | 2026-03-24 | Cloud Infra Upgrade | Arjun Kapoor | Blocked | Low | 19
TSK-1146 | Train reporting module | 2026-01-03 | 2026-01-25 | Website Revamp | Sneha Iyer | In Progress | High | 47
TSK-1147 | Design reporting module | 2026-01-30 | 2026-02-22 | Mobile App Launch | Aditi Sharma | In Progress | Low | 56
TSK-1148 | Integrate third-party integration | 2025-12-30 | 2026-01-27 | Marketing Automation | Aditi Sharma | In Progress | Low | 23
TSK-1149 | Audit email templates | 2026-01-26 | 2026-02-19 | Q3 Product Release | Neha Gupta | In Progress | Medium | 20
TSK-1150 | Configure user authentication | 2026-04-02 | 2026-04-19 | Marketing Automation | Farhan Khan | Not Started | Medium | 0
TSK-1151 | Test backup process | 2026-01-07 | 2026-01-14 | Vendor Onboarding | Farhan Khan | Not Started | Low | 0
TSK-1152 | Migrate onboarding flow | 2026-03-27 | 2026-04-17 | Q3 Product Release | Anjali Rao | Completed | Critical | 100
TSK-1153 | Plan dashboard layout | 2026-04-21 | 2026-05-19 | Mobile App Launch | Rohan Mehta | Completed | High | 100
TSK-1154 | Audit user authentication | 2026-03-27 | 2026-04-13 | Data Warehouse Build | Farhan Khan | In Progress | High | 68
TSK-1155 | Develop database schema | 2026-01-09 | 2026-02-04 | Q3 Product Release | Anjali Rao | In Progress | Medium | 75
TSK-1156 | Test data pipeline | 2026-03-06 | 2026-04-05 | Mobile App Launch | Rohan Mehta | Completed | Medium | 100
TSK-1157 | Document onboarding flow | 2026-01-01 | 2026-01-19 | Website Revamp | Arjun Kapoor | Completed | Critical | 100
TSK-1158 | Test performance metrics | 2026-04-27 | 2026-05-18 | Website Revamp | Sneha Iyer | In Progress | Medium | 42
TSK-1159 | Deploy access controls | 2025-12-30 | 2026-01-28 | Cloud Infra Upgrade | Rohan Mehta | Completed | Medium | 100
TSK-1160 | Finalize backup process | 2026-04-22 | 2026-04-27 | Cloud Infra Upgrade | Anjali Rao | Delayed | High | 58
TSK-1161 | Design reporting module | 2026-02-25 | 2026-03-13 | Website Revamp | Priya Nair | Completed | Medium | 100
TSK-1162 | Audit email templates | 2025-12-08 | 2025-12-15 | CRM Migration | Arjun Kapoor | Not Started | High | 0
TSK-1163 | Train access controls | 2026-03-05 | 2026-03-19 | Cloud Infra Upgrade | Anjali Rao | In Progress | Medium | 56
TSK-1164 | Develop backup process | 2025-12-13 | 2026-01-08 | Mobile App Launch | Aditi Sharma | Completed | Low | 100
TSK-1165 | Develop release notes | 2026-02-08 | 2026-02-19 | Vendor Onboarding | Anjali Rao | In Progress | Medium | 80
TSK-1166 | Optimize server setup | 2026-04-04 | 2026-04-25 | Data Warehouse Build | Rohan Mehta | Completed | Medium | 100
TSK-1167 | Deploy dashboard layout | 2025-12-02 | 2025-12-13 | Website Revamp | Karan Verma | Completed | Medium | 100
TSK-1168 | Test payment gateway | 2026-04-07 | 2026-05-05 | CRM Migration | Sneha Iyer | In Progress | Medium | 70
TSK-1169 | Configure API endpoints | 2026-03-01 | 2026-03-08 | Data Warehouse Build | Neha Gupta | Completed | High | 100
TSK-1170 | Configure access controls | 2026-02-19 | 2026-03-14 | Data Warehouse Build | Aditi Sharma | Not Started | Medium | 0
TSK-1171 | Plan release notes | 2026-02-22 | 2026-03-04 | Data Warehouse Build | Anjali Rao | In Progress | Medium | 73
TSK-1172 | Develop user feedback | 2026-04-30 | 2026-05-17 | Mobile App Launch | Anjali Rao | In Progress | High | 82
TSK-1173 | Optimize user authentication | 2025-12-20 | 2026-01-10 | Marketing Automation | Vikram Singh | Completed | Low | 100
TSK-1174 | Test backup process | 2026-01-07 | 2026-01-19 | Cloud Infra Upgrade | Vikram Singh | Delayed | Medium | 26
TSK-1175 | Train performance metrics | 2025-12-20 | 2025-12-30 | Cloud Infra Upgrade | Priya Nair | Completed | Medium | 100
TSK-1176 | Plan test cases | 2026-04-24 | 2026-05-19 | Vendor Onboarding | Arjun Kapoor | In Progress | High | 56
TSK-1177 | Migrate API endpoints | 2026-02-16 | 2026-03-18 | CRM Migration | Farhan Khan | In Progress | Low | 50
TSK-1178 | Plan server setup | 2025-12-10 | 2025-12-16 | Q3 Product Release | Neha Gupta | In Progress | Low | 62
TSK-1179 | Analyze API endpoints | 2026-03-29 | 2026-04-21 | Mobile App Launch | Rohan Mehta | Completed | Medium | 100
TSK-1180 | Design third-party integration | 2026-04-01 | 2026-04-22 | Vendor Onboarding | Arjun Kapoor | In Progress | High | 34